## CoS_RACI
RACI
| Project | [6 empty] | OTTO ID#
| Project Manager | [6 empty] | Spend ($)
| PEPxxxxxR/E | [6 empty] | Productivity ($)
| Project Deliverables |  | Asterisk (*): refers to projects he /she owns due to Commodity or Site support. Deliverable Description. | PES | CoS. | QVE | Global Commodity Director | Regional Commodity Mgr. | Project Specialist Mgr. | Project Specialist (PS) | Business Unit Partner | Procurement Mgr. | Category Buyer | Cluster Procurement Mgr. | MPL | PM´s Mgr. (SBO-REB) | Initiative Management Coordinator | Project Manager (PM) | Project Enngineering Manager | Project Engineer (PE) | CE | SQE Manager | SQE | Core Tech Mgr. | Core Tech Eng. | Supplier Development Mgr. | Supplier Development Sppecialist | S3L | Plant Buyer.
CoS (Pre-Work)
1 | 1 | Set Strategy. | ▪Where to buy? ▪Provide list of part numbers along with supplier name that maximize benefits to SE. (Supplier should be align to Commodity Strategy). |  | Y | Y | A | R | I |  |  | S | S | I | I | I | [5 empty] | C |  |  |  | C-I
2 | 2 | Idea in MOVE | ▪Get Idea at Initial Review phase. (Draft Status or Initial Review, Data Validation etc.). | Y | Y | Y |  |  | A* | R |  | A* | R | A* | R/S |  |  |  |  | C
3 | 3 | Supplier Status (SAM & SRiM) | ▪Assure supplier is at Green Status in SAM and SRiM. ▪If supplier is in Yellow status be sure an action plan is set to move supplier from Yellow to Green Status. ▪Request audit if SAM and/or SRiM is/are not available. | Y | Y | Y |  | I |  | R* |  | S | R* |  | S | [6 empty] | A | R
4 | 4 | Data gathering for RFQ | ▪BOMs, Volume, Forecast Y+1 (Next Year), design spec, SE Plant involved. |  | Y | Y |  | C-I | A* | R |  | A* | R | A* | S/R* |  |  |  |  | C |  | C
5 | 5 | Ariba Event | ▪Sent Ariba event to Supplier for quoting. | Y | Y | Y |  | C-I | A* | R |  | A* | R | A* | S/R*
6 | 6 | RFP Analysis | ▪Maximize benefits (price part, logistic, lead time etc) per supplier quote. ▪Select best supplier to buy. | Y | Y | Y |  | C-I | A* | R | I | A* | R | A*/I | S/R* |  |  |  |  | C
7 | 7 | Supplier Award | ▪Sent Award to supplier. | Y | Y | Y |  | A |  | R | I | I | R | A*/I | R | I |  |  | I |  |  | I |  | I |  | I |  | R
REQUEST (OTTO: START, CF=0%)
1 | 8 | PR (Project Request) | ▪Delivering a solid Project Business Case, (Total Cost Ownership -TCO- for each part.) ▪Project Business case includes details of total project cost and benefits. | Y | Y | Y |  |  | A* | R |  | A* | R | A*/I | S/R* |  |  |  | C | C |  | I
2 | 9 | Resource allocation (Steering Committee) | ▪Assure resources are allocated by Functional Mgrs. | Y | Y | Y | [9 empty] | R | A |  | R |  |  | R | bar: A*; I; A*/I
3 | 10 | Core Team reviews PR | ▪Core Team (Initiative Management Coordinator) reviews PR |  | Y | Y |  | R | R | R |  |  | R | A*/I | S/R* |  | A |  | R-C |  |  | R-C |  | C
4 | 11 | Project in OTTO | ▪Upload project in OTTO and get OTTO ID #. ▪Not mandatory for all. | Y | Y | Y | [9 empty] | I |  | A |  |  |  | I | bar: R; A* to S/R*
Identification & Diagnostic (OTTO:RFQ, CF=0%)
1 | 12 | Core Team Kick-off Meeting. | ▪PM/¨Project Lead sets meeting with Core Team members. ▪Proactively each team members identify potential gaps, misses, risk, best practice related to its own or other deliverables. ▪At the end of meeting is expected each Core team members have a clear understanding of all their own deliverables and sets a pre-work list of deliverables to be included in timeline. | Y | Y | Y |  |  |  |  | I | A* | S/R* | A* | S/R* | C-I |  | A-R |  | S |  |  | S |  | S
2 | 13 | PE- prework | ▪Per Core Team meeting held previously. PE identifies and gather all info related to its own deliverables such as: Drawings, 3D, Specs., CQCS etc. |  | Y | Y | [11 empty] | I | A | R |  |  | I | [6 empty] | Responsible | The person who performs the deliverable
3 | 14 | MPL Pre-work | ▪Per Core Team meeting held previously. MPL identifies and gather all info related to its own deliverables such as; Inventory levels: On-hand, In-Transit, PO placed, etc.( Electronics Cluster, procurement plant provides inventory levels); Part numbers obsolescence, where used, LoB impacted. |  | Y | Y | [11 empty] | I | [10 empty] | R | Accountable | The person held accuntable to ensure deliverable is completed | bar: S/R*
4 | 15 | SQE Pre-work | ▪Per Core Team meeting held previously. SQE identifies and gather all info related to its own deliverables such as: Deviation, quality issues/complaints, Incoming Insp, CQCP. |  | Y | Y | [11 empty] | I |  | I |  | A | R | [6 empty] | Support | The person who helps/supports to perform deliverable.
5 | 16 | Category Buyer-pre-work | ▪Per Core Team meeting held previously. Category Buyer identifies and gather all info related to its own deliverables such as: Business case (PCR), Pricing LTs & MOQs confirmed w/Supplier, Legal docs validation (NDA, QSP, MSA, etc.), Equipment required by supplier with cost details, Incoterms confirmation, SAM & SRiM validation. | [14 empty] | I | bar: A* to R
6 | 17 | Core-Tech pre-work (Tooling Assessment). | ▪Per Core Team meeting held previously. Core Tech identifies and gather all info related to its own deliverables such as: Tooling Assessment, etc. |  | Y | Y | [11 empty] | I |  | I |  |  | I | A | R |  |  |  |  | Consulted | The person(s) consulted before to perform deliverable.
8 | 18 | BoC Blitz (If Apply) | ▪If BoC blitz apply. Review of CAPEX and OPEX defined in PR with BoC Admin. ▪Per BoC Admin input, CAPEX and OPEX are reviewed and updated. |  | Y | Y |  |  | I | R | S |  | C/R* |  | S/R* | C-I |  | A-R | C |  |  | C |  |  | C
7 | 19 | PR (Review, Challenge, Clarify) | ▪Deep review to project request (PR). ▪Whole undersanding of project cost/ project benefits (Value added for SE). ▪Understand strategy, critical path, risk(s), best practices etc. ▪At the end is expected PM and Core Team commit to deliver project benefits described in PR and adherence to project cost. | Y | Y | Y |  | R: C; R: C; S/R*: C/R* | I | C | A-R |  | C | [9 empty] | Informed | The person(s) informed before/after to perform deliverable.
9 | 20 | BoC OPEN | ▪PM prepares for OPEN (Docs, presentations etc.) ▪Scheduled OPEN DATE. |  | Y | Y |  | C |  | C | C |  | C/R* | I | S/R* | A |  | R |  | C |  | C |  |  | C
10 | 21 | PR Updated (If apply) | ▪PR updated per PR review, challenge, clarify and BoC blitz. |  | Y | Y |  | R: R; I: I; R: C/R*; S/R*: S/R* | I |  | A |  | I |  |  | I |  | I
11 | 22 | PR in TEMPO | ▪ Upload PR in TEMPO an get PEPxxxxxxR. | Y | Y | Y |  | R: R; I: I; R: R; S/R*: R* |  |  | A
12 | 23 | Project Risk Management/Lessons learned | ▪PM/Project Lead identify project risk(s), review with peers best practices/lessons learned (similar projects, suppliers etc.). | Y | Y | Y |  | R: C/R*; A*/I: I; S/R*: S/R* | A |  | R |  | I |  |  | I |  | I
12 | 24 | Project Status Report | ▪PM gets regular project status report meeting with stakeholder (weekly, bi-weekly, monthly) to assure stakeholder engagement, alignment, commitments. | Y | Y | Y |  | I: I; R: C/R*; A*/I: I; S/R*: S/R* | A |  | R |  | I |  |  | I |  | I
OPEN (OTTO: LOI, CF=20%)
1 | 25 | OPEN PROJECT APPROVAL (Go-NO Go decision) | ▪ Get OPEN project approval from BoC | Y | Y | Y |  | I |  | I | I | I | I/R* | I | S/R* | A |  | R | I |  |  | I |  | I
Feasibility & Impact (OTTO: LOI, CF=20%)
1 | 26 | OTTO Records updated/confirm | ▪ Once OPEN project is awarded, confirm or update OTTO Record (Volume, Price, P&L date etc.). | Y | Y | Y |  |  |  |  | I | A* | S/R* | A* | R | I |  | A
2 | 27 | Kick-off meeting (Core & Extended Team). | ▪ PM schedules a kick-off meeting with main stakeholder to show project scope, cost, schedule (gates, phases etc.), risks, communication (project status, team interaction etc.). ▪ Invite Plant Manager and Plant staff. | Y | Y | Y |  | I: I; A*: A*; R: R*-S; S/R*: A*-R |  |  | A-R |  | R |  |  | C |  | C
3 | 28 | Process & Tooling info (Current Supplier) | ▪ Core Tech gets tooling condition from current supplier. |  | Y | Y | [9 empty] | I |  |  |  | I |  |  | I | A | R | bar: R; S/R*
4 | 29 | BCFE (If apply). | ▪ Submit and gets formal BCFE approval. |  | Y | Y |  | R: A*-R*; A*/I: A*; S/R*: S-R* |  |  | A-R | [6 empty] | R
5 | 30 | Inventory levels: On Hand, In-Transit, PO placed | ▪ Get Inventory levels of part numbers impacted: On-Hand, In transit, PO placed. ▪ Per inventory levels assess best strategy to execute project. | Y | Y | Y |  | R: A*-S; S/R*: A* |  |  | A | [10 empty] | R
6 | 31 | LAIR (report) | ▪ Gets current dimensional part number condition from current supplier. |  | Y | Y | [11 empty] | A |  | I |  |  | R |  | I | bar: S/R*
7 | 32 | LAIR agreeement (New PPEP directive --approval against LAIR, follow transfer policy) | ▪ Based on LAIR: A)LAIR = Drawing. B)LAIR is different from drawing. PE gets agreeement with CE how part number will get approval from FAIR (dimensional report from new supplier). |  | Y | Y | [11 empty] | A |  | R |  |  | R |  | I | bar: S/R*
8 | 33 | Reverse Engineering decision (New tooling, transferir with current condition) | ▪ PE decides if reverse engineering is needed. |  | Y | Y | [11 empty] | I |  | A-R |  |  | C | bar: S/R*
9 | 34 | Inventory Build-up Plan | ▪ Based on inventory levels and current demand, it is decides the build-up inventory from current supplier before transfer tooling to new supplier. | Y | Y | Y |  | R: A*-R; S/R*: A* |  |  | A |  | I |  |  | I |  | I |  |  |  | R
10 | 35 | PPEP, SE (Requirements, approvals). | ▪Part requirements are recorded from functional areas in PPEP database. | Y | Y | Y |  | R: S/R*; S/R*: R |  |  | I |  | R |  |  | A-R |  | R
11 | 36 | Measurement test Method (SE- New Supplier) | ▪Assure supplier test measurement system is analogous (similar) to SE measurement system. ▪Same parts from LAIR measured in SE can be sent to new supplier for LAIR measurment. |  | Y | Y | [13 empty] | C |  |  | A-R |  | C | C
12 | 37 | CQCS | ▪ List of characteristics to control, established by the Design in order to ensure Product Quality and Safety. ▪PE created CQCS (Component Quality Control Specification). ▪Mandatory for CRITICAL PARTS. ▪CQCS shall be recorded in SYMPHONY. |  | Y | Y | [11 empty] | I | A | R |  |  | I |  | I | bar: R
13 | 38 | CQCP | ▪ SQE performs Component Quality Control Plan (CQCP) per CQCS input. |  | Y | Y | [11 empty] | I |  |  |  | A | R |  | I | bar: R
14 | 39 | Validation Plan | ▪ Part requirements are documented in PPEP database from all functional areas. |  | Y | Y | [11 empty] | I | A | R |  |  | I | bar: R; S/R*
15 | 40 | Set incoming inspection for build-up | ▪ Assure part numbers from build-up are checked at Incoming Inspection.This action will assure to have good parts during tooling transfer. |  | Y | Y |  | R: R*; S/R*: A*/I |  |  | A |  |  |  |  | R
16 | 41 | PPEP (Records, review with supplier, Signoff) | ▪ PPEP requirement are sent to new supplier for acknowledge and commitment to meet requirements set in PPEP document. ▪PPEP cover signed-off by new supplier. |  | Y | Y |  | R: S/I*; S/R*: R/R* |  |  | I |  | I |  |  | A |  | I
17 | 42 | TEMPO Management | ▪ Update PR and related documents in TEMPO database. | Y | Y | Y | [11 empty] | A | bar: R; R; S/R*
DO-IMPLEMENT (OTTO: COS:SAR, CF=50%)
1 | 43 | BoC DO approval | ▪ Get DO-IMPLEMENT project approval from BoC | Y | Y | Y |  |  |  |  | I | I | A*/R | I | R* | I |  | A-R | I |  |  | I |  | I
2 | 44 | Project Commitment (Timeline, P&L date, Action Exec. Date) PMO, KPIs = SBO, Productivity, Rebalancing, On time Project Execution. | ▪Project Team (PM/Project lead along with Core Team) commits to deliverables assigned in Timeline. ▪Project team commits to P&L date, Productivity, Rebalancing (On Time Project Execution). |  | Y | Y |  |  |  |  | I | C-I | A*/R | C-I | A*/R | C-I |  | A-R | C-I | R |  | C-I | R | C-I | R
Product & Process Design (OTTO:SAR, CF=50%) / Implementation & Validation (OTTO: SAQ, CF=75%)
1 | 45 | OTTO Records updated. | ▪ Once DO-IMPLEMENT project is awarded, confirm or update OTTO Record (Volume, Price, P&L date etc.). | Y | Y | Y |  | A*: A*; R: S/R*; A*/I: A*; S/R*: R | I |  | A | [12 empty] | A
2 | 46 | Reverse Engineering execution (If Apply) | ▪ PE executes reverse engineering plan set in Feasibility & Impact phase. |  | Y | Y | [11 empty] | I | A | R |  | I | C |  | C | bar: S/R*
3 | 47 | Tooling transfer | ▪ Tooling(s) are transfer to new supplier. |  | Y | Y |  | R: S; S/R*: I/S |  |  | A |  | I |  |  | I |  | R
4 | 48 | Process Parameters | ▪Supplier process capability & controls ensures design requirements are met through the part product life cycle. ▪ Assure all process parameters from new supplier are identified, recorded and monitored (control plan). |  | Y | Y | [11 empty] | I |  |  |  |  | C |  | A-R | bar: R; S/R*
5 | 49 | Tool Design approval | ▪ Assure to get Tool design approval before get samples for validation. |  | Y | Y | [11 empty] | I |  | I |  |  | I |  | A-R | bar: R; S/R*
6 | 50 | Test flow | ▪ Submit Test Flow for testing. |  | Y | Y | [11 empty] | I |  | A-R |  |  | I
7 | 51 | Samples (piece part, Sub-Assy, Finished God). | ▪ Get samples from new supplier and delivery to Lab or others destinations to execute validation plan (3F, Metallography, electrical testing, salt spray etc.). |  | Y | Y |  | R: A*-S; S/R*: R |  |  | A-I |  | C-I |  |  | I
8 | 52 | Test Report (other labs -not FAIR-) | ▪ Get test report from testing executed in labs (metallography, electrical test, endurance test etc.). |  | Y | Y | [11 empty] | I |  | A-R |  |  | I | bar: R; S/R*
9 | 55 | FAIR (report) | ▪ Get dimensional report from new supplier parts (FAIR). |  | Y | Y | [11 empty] | I |  | I | I |  | A-R | bar: R; S/R*
10 | 54 | FAIR disposition | ▪ Get CE FAIR approval disposition. |  | Y | Y |  | R: I; S/R*: A*/I |  |  | I |  | A | R
11 | 55 | 3F´s & Test Assy approval | ▪ At part level and/or Sub-assy and/or Assy perform fit, form and function. |  | Y | Y |  | R: I; S/R*: A*/I |  |  | I |  | A | R
12 | 56 | PPEP item(s) approval | ▪ Per PPEP requirements and test results team members from functional areas approve PPEP. | Y | Y | Y |  | R: A*/R; S/R*: A*/R |  |  | A |  |  | R |  | R |  | R
13 | 57 | Final PPEP sign-off | ▪ SQE confirm all requirements from PPEP are covered (SE inputs, Supplier deliverables, SE approval process). | Y | Y | Y | [11 empty] | I |  |  | I |  | A-R |  | I | bar: R; S/R*
14 | 58 | Record PPEP doc in Symphony (Global RACI) | ▪ PPEP approved is uploaded in Symphony. |  | Y | Y | [14 empty] | R |  | A | bar: R; S/R*
15 | 59 | Design Docs Updated (Symphony) | ▪ Engineering docs per PPEP approval are uploaded/updated in Symphony. |  | Y | Y | [11 empty] | I |  | A-R | bar: R; S/R*
16 | 60 | Contract Agreement | ▪ Tooling contract agreement among SE and Supplier. | Y | Y | Y |  | C-I: A-R; R: S; A*/I: I; S/R*: I |  |  | I
17 | 61 | Inventory levels: On Hand, In-Transit, PO placed | ▪ Get Inventory levels of part numbers impacted: On-Hand, In transit, PO placed. ▪ Per inventory levels defined best P&L impact date as well as productivity impact for current year (savings). | Y | Y | Y |  | R: A*-R; S/R*: A* |  |  | A | [10 empty] | R
18 | 62 | Ramp-up Plan | ▪ Per inventory levels and current demand set best ramp-up plan strategy. | Y | Y | Y |  | R: A*-R; S/R*: A*/R | I |  | A | [6 empty] | I |  |  |  | R
19 | 63 | OTTO Records (Action Exec. Date, P&L date) | ▪ Confirm or update OTTO Record (Volume, Price, P&L date, Action Exec. Date, etc.). | Y | Y | Y |  |  |  |  | I | A* | S/R* | A* | R | I |  | A
PRODUCE-SELL (OTTO: COS-TAP, CF=75%)
1 | 64 | BoC PRODUCE-SELL | ▪ Get PRODUCE-SELL project approval from BoC | Y | Y | Y |  |  |  |  | I | I | A*/R | I | A*/R | I |  | A-R | I |  |  | I |  | I
Production (OTTO:COS-TAP, CF=75%) / Assessment Closure (OTTO: ON-CONTROL, CF=75%)
1 | 65 | OTTO Records updated. | ▪ Once PRODUCE-SELL project is awarded, confirm or update OTTO Record (Volume, Price, P&L date, CF etc.). | Y | Y | Y |  | A*: A*; R: S/R*; A*/I: A*; S/R*: R | I |  | A
2 | 66 | Materials Resource Planning (MRP) setting. One-Shuttle, Work-Flow (Functional areas requirements). | ▪ Launch One-Shuttle or other applicable process to assure new supplier parameters (lead-time, MOQ, Price, Packaging size etc.) are set in. |  | Y | Y |  | R: S; S/R*: A*/R |  |  | I | [10 empty] | R
3 | 67 | Ramp up / Ramp down execution | ▪Monitor/assure Savings/month forecasted is executed per OTTO record(s). ▪Detect deviation per productivity plan. | Y | Y | Y |  | R: A*/R; S/R*: A*/R |  |  | A | [10 empty] | R
4 | 68 | First production lot. | ▪ Issue first production lot to new supplier |  | Y | Y |  | R: A*; S/R*: A*/R |  |  | A | [10 empty] | R
5 | 69 | Productivity comparison (Plan vs Real) | ▪ Sell gate, compare actual results vs original business case. | Y | Y | Y |  | I: I; R: C/R*; S/R*: R* | A |  | R
6 | 70 | Close activities from Implementation/Validation (UL, Design Records, Stakeholders) | ▪ Assure all deliverables are completed from all functional areas before receipt of part from new supplier; e.g., from engineering (standard validation plan, design records updated, Kanban updated etc.). |  | Y | Y |  | R: A*/S; S/R*: R |  |  | A |  | R |  |  | R |  | R |  |  |  | R
7 | 71 | Lessons Learned, Best Practices | ▪PM along with Core Team members document best practices and lessons learned for future reference in the Strategic Project Portal Knowledge Base (lesson learned database and more). | Y | Y | Y |  | I | I | R |  | I | A*-R | I | R | I |  | A-R | I | R |  | I | R | I | R
CLOSE (OTTO: ON-CONTROL, CF=100%)
1 | 72 | BoC Close | ▪ Get CLOSE project approval from BoC | Y | Y | Y |  |  |  |  | I | I | A*/R* | I | R* | I |  | A-R | I |  |  | I |  | I
Note on R6: -PM Core Team Leader-
Note on AC6: Support Commodity Mfr (Global position)
Note on U14: If there is/are a deviation from design
Note on B24: Identification & Diagnostic. Preparation phase to elaborate a formal request to the BoC (Board of Change) in order to provide an assessment of the bnefits, risk & impact for the BoC decision.
Note on C34: Preparate for OPEN (Docs, presentations etc.) Scheduled OPEN DATE.
Note on B44: Feasibility & Impact. Investigation and feasibility activities to reach an agreement on a proposal change between all internal/external interested parties.
Note on C48: CAPEX
Note on C51: Per Ricardo comments, Part approval taking as reference LAIR, when there´s no validation plan. Deployment on July, August.
Note on X51: Agreeement by SQE in characteristics to be measured.
Note on P60: Per Ceci also applies when MPL lead the project.
Note on P61: E Cluster Tempo: Vicotria, Portland, Clovis
Note on E64: Go, NO Go decision
Note on B67: Product & Process Design. Design the product and its related process, reach sufficient confidence to decide to launch modifications of tools & equipment. Implementation - Validation Create and verify the physical parts or products (manufactured samples). Qualify the modification of the supply chain (pilot run)
Note on P70: E-Cluster. There is PM act as support
Note on C71: Check-list from Core Tech.
Note on E91: Go, NO Go decision
Note on B94: Production. End or scrap all former stocks. Supply new components stocks. Asssessment & Closure. Start Production. Review implementation in all plants and objectives attainment.
Note on E105: Go, NO Go decision